## All actions
HR Excellence in Research Action Plan 2018-20 January 2018 (Revised 6th June 2018)
Principle 1: RECRUITMENT AND SELECTION
Recognition of the importance of recruiting, selecting and retaining researchers with the highest potential to achieve excellence in research.
Sub principle | Action | Lead | Supported by: | Success Criteria | Timescale | Summary of progress
2. Employers should strive to attract excellence and respect diversity (see Principle 6). Recruitment and selection procedures should be informative, transparent and open to all qualified applicants regardless of background. Person and vacancy specifications must clearly identify the skills required for the post and these requirements should be relevant to the role. | Recruitment processes must reflect the University’s standard on diversity and inclusion and appropriate to research recruitment (clear specification, etc.). | HRD - Head of Resourcing | HR Resourcing EDI | Recruitment and selection in line with funding council requirements and University commitment to E&D. E&D reports to evidence delivery of action. | Annual review, Sept 2018, 2019 | ·Job descriptions are clear and language is modified to be gender neutral. Person specification present and part of the Job description. All recruiting managers are reminded of their duties to hold a fair, transparent and quality focused process. Consideration for part-time / flexible working to be applied (where operationally relevant). ·Revised Diversity Text has been added to all Job Adverts - "...At Hull we are committed to equality of opportunity, diversity and inclusion at every level, because we believe a diverse workforce brings broader expertise, improved innovation and greater success for all...". ·Information collated via the Stonefish platform. Recruitment & Contracts Team manually track the following: quantity of submitted applications and also quantity of female applicants, females shortlisted, females appointed. Likewise, if a Disability Confident candidate has applied and has provided this information. ·We attach a generic brochure to all our posts which promotes and showcases the University to all prospective candidates. The brochure is informative and inclusive in language and tone. Trialling 'textio' an augmented writing platform - to unlock language.
| Advice to PIs on naming researchers at the point of application for funding is consistently applied in line with University Recruitment and Selection policies. | Deans | ADR, DoR |  | Annual Review, Dec 2018, 2019 | PIs and faculty Research Development Managers work with HR and the RFO to ensure compliance with University Recruitment and Selection policies. PIs are also expected to undertake mandatory training in Diversity in the Workplace, and Recruitment and Selection. Monitored via Worktribe checks. This is now considered to be business as usual. Periodic reminders are sent to PIs.
4. To assure fairness, consistency and the best assessment of the candidates’ potential, recruitment and progression panels should reflect diversity as well as a range of experience and expertise. In order to promote these values, individuals who are members of recruitment and promotion panels should have received relevant recent training. Unsuccessful applicants should be given appropriate feedback if requested as this may be of assistance to the researcher in considering their further career development. | University recruitment processes to be fully applied to all roles | HRD - Head of Resourcing | HR Resourcing | All Chairs of panels to have had appropriate training. | Ongoing as new chairs appointed | All new recruiting managers are required to undertake the online learning module (with a 3 yearly refresh cycle). The HR Resourcing team check the suitability and diversity of each panel and challenge those who need to undertake / refresh their training alongside their responsibility to conduct a fair, open and quality focused recruitment exercise. This includes having diversity of gender on the panel. Recruitment and Contract Team manually check / track panel gender (monitoring for single gender panels). Recruiting managers are challenged in order to mitigate use of single gender panels. All Panel Members must have completed R&S e-learning module (refreshed on a 3 year cycle). The Chair of the panel must have undertaken 'unconscious bias' training, again monitored by the R&C team. We actively ensure mixed gender panel composition. At Hull we experience a challenge with wider panel diversity (BME) due to the workforce profile. In the last 12 months there were a total of 420 panels. No panels were all male and only six panels all female and related to administrative and manual jobs. Note managers will be able to monitor staff training through I-Trent Manager Self-Service function.
| All recruitment panel members receive training before taking part in recruitment | HRD - Head of Resourcing | HR Resourcing | Online training registers maintained by L&D | Ongoing as new panel members appointed | Learning events attendance reporting function available through HUMID (Hull University Management Information and Data). Completion of R&S online and unconscious bias online / face to face workshops is added to I-Trent (HR and Payroll system, provided by Midland Trent). Face to face unconscious bias training reintroduced to the 2018/19 portfolio to enhance the existing online course and provide an alternative learning form for staff. For impartiality and an understanding of the basics required within the recruiting process - all members (who are directly engaged by Hull) and sitting on a panel should have accessed and completed the online e-learning.
| Review the need for further training on providing tailored feedback to unsuccessful candidates | HRD - Head of Resourcing | HR Resourcing | When requested, unsuccessful candidates are provided with appropriate constructive feedback tailored to the role and aligned to the RDF. | Annual Review, Sept 2018, 2019 | Revised guidance on providing feedback to unsuccessful candidates has been drafted for inclusion in the revised Recruitment & Selection Procedures (presently with HR Leadership Group before moving through to Policy Working Group). In the interim period this guidance is shared with Chairs of panel when unsuccessful candidates request feedback through the HR Administrator coordinating the post. Current guidance still provides supporting information/signposting to effective feedback. Reinforced in the online R&S module. Any requests for feedback are directed to the relevant hiring manager/panel Chair.
Principle 2: RECOGNITION AND VALUE
Researchers are recognised and valued by their employing organisation as an essential part of their organisation's human resources and a key component of their overall strategy to develop and deliver world-class research.
Sub principle | Action | Lead | Supported by: | Success Criteria | Timescale
1. Employers are encouraged to value and afford equal treatment to all researchers, regardless of whether they are employed on a fixed term or similar contract. In particular, employers should ensure that the development of researchers is not undermined by instability of employment contracts. This approach should be embedded throughout all departmental structures and systems. | Faculties to continue to work towards ensuring equality of opportunity across the research employees’ experience. | Deans | HoD ADRs | Staff survey (2018) and CROS/PIRLS 2019 will demonstrate improving scores in perceptions of equality of opportunity (increase to 30% in CROS2019) Responses to CROS survey questions relating to being fairly treated at work, with access to training and development, increase to an average of 85% positive responses. | Review point October 2018, CROS/PIRLS2019 CROS2019 | In CROS 2019, 87% of respondents believed that the University is committed to equality and diversity (compared to 80% in 2017). 76% of respondents felt staff were treated fairly, regardless of personal characteristics, in relation to access to training and development and 74% with regard to day-to-day treatment. Equality of opportunity is built into faculty research strategies and Athena SWAN application plans. All research employees should undergo local induction and be encouraged to attend central induction to the University. In addition to mandatory training, staff are informed of and encouraged to make use of staff development opportunities, internally and externally. Training and development is addressed in appraisals. While 76% of CROS2019 respondents indicated that they were satisfied that research staff were treated fairly with regards to training and development, 15% did not know and 9% disagreed. Using the FSE as an illustration : this is reflected in feedback reported by FSE indicating that some researchers felt that they were less fairly treated than permanent staff in this respect. FSE is combatting this via delivering: 1. a dedicated PDRA teaching module to offer lecturing experience to remove barriers to earning first lectureship positions and to promotion within research grades; 2. Research Excellence Awards which recognise contributions by researchers at all levels via open nominations from colleagues; 3. opportunities for training on writing grants via ThinkWrite (external providers); 4. opportunities for training on writing papers have taken place via external training company ThinkWrite; 5. mentoring programme open to all academics within the Faculty designed to provide focused mentoring for areas of development identified by mentees; 6. access to faculty-funded writing retreats which offer dedicated time away from campus to write papers or grants; 7. Additional induction to be provided to PDRAs emphasising the availability and importance of learning and development and the right of PDRAs to access it equally. Need further monitoring to assess effectiveness of these interventions. Similar initiatives occur across the Faculties.
| Ensure evidence from training records available for researchers on both Continuing and Fixed Term Contracts. | Head of L&D |  | Research staff can clearly be identified in the i-Trent database. Functionality of i-Trent will be increased in future to allow training records to be reviewed by their line-manager. | Annual Review Sept 2018 and 2019 | L&D: Mandatory training and learning attendance reports are available through HUMID and populated by L&D. Reports can be compiled by area / contract / individual. My-HR manager functionality sits with the I-Trent team who have plans in place to provide managers access to their staff members training records. L&D: Protocols agreed for recording Data Protection, EDI and Research Integrity training. Frequency and distribution list agreed. University-approved secure cloud storage (Box) will be utilised for sharing data and institutional summaries provided to Deans and Directors.
| HR Partners to conduct spot check audits of 10% of researchers’ records to ensure that attendance on development courses is not undermined by stability in working contract. | HR Partners. |  | 1. Hours of training recorded for researchers will reflect their individual needs as identified through appraisal/review. 2. Researchers on STCs will have similar training records to research staff on permanent contracts in terms of total hours of training recorded. | Annual review Sept 2018 and 2019 | HR Partners have carried out annual spot checks and the results indicate that those researchers on FTC's have the same level of access and take up of learning and development opportunities as those on continuing contracts. Going forwards, the revised Concordat has recommended that researchers should spend a minimum of 10 days per annum on training and development and this will need to be monitored.
3. Research managers should be required to participate in active performance management, including career development guidance, and supervision of those who work in their teams. Employers should ensure that research managers are made aware of, and understand their responsibilities for the management of researchers and should provide training opportunities, including equality and diversity training, to support research managers in doing this. Institutions will wish to consider how research managers’ performance in these areas is developed, assessed and rewarded, and how effectively this supports good research management. | To provide leadership and management skills training (including equality and diversity training) for research managers, acknowledging existing areas of good practice. | Head of L&D | ADRs | Annual review of L&D course provision | Annual review 01/02/2018, 01/02/2019 | L&D offer a wide portfolio of leadership and management development activity available to research managers and the portfolio is reviewed annually. Planning meeting is held annually in February, with portfolio development taking place in time for launch at the beginning of the academic year. In addition L&D host a managers' network and are currently consulting about the interest in forming a research staff association, which could offer opportunities for gaining experience in a leadership role. The Leadership for Hull programme for Heads of Department was launched in September 2019. The programme includes taught modules and peer learning sets. In addition the Heads have formed their own 'network' led by two of their members. The University participates in the Aurora programme. Research managers and leaders for participation in leadership courses are identified at Faculty level. Faculties share best practice and information about training and development opportunities by email and via meetings. Faculties lead on other initiatives e.g. FSE provided dedicated training for research managers in 2018 from Advance HE on leadership for research managers and has supported 5 participants for the Aurora leadership programme in 2019/20.
|  |  |  | Records show 85% compliance with equality and diversity training | Annual review, Sep 2018, 2019 | Equality and Diversity training is mandatory for all staff and is available in three online formats and face-to-face through the EDI Essentials training. L&D are rolling out 'Train the Trainer' activity to expand the pool of EDI Essentials training, providing additional skilled resource to manage the high levels of demand for EDI training. 'Train the Trainer' activity completed with five University staff now able to deliver EDI essentials training to bespoke groups. HUMID reports indicate that compliance has increased from 58% in 2018, to 64% in April 2019 to 71% in October 2019. The target is 85% compliance and regular eBulletin communications are planned regarding the requirement to complete all mandatory training. Review of E&D training underway to ensure that all managers have completed this.
| Ensure all research managers attend leadership and management skills courses | Deans | ADRs | Recently appointed Research Managers nominated by Deans, invited and enrolled in the Leadership@hull development programme. | Review 01/12/2018,01/12/2019 | Two cohorts of about 20 people took up the offer of the Leadership@hull programme in 2017. The programme has been reviewed and relaunched as Leadership4Hull in September 2019, again with about 20 participants. Faculties have appointed Faculty research managers and reviewed leadership development needs. For example, FSE made an open call for expressions of interest invited for attendance on Research Team Leaders development delivered by Advance HE. Positive feedback was received regarding the skills and techniques learned. Also faculties have supported participants on the Aurora (women leadership) programme. Managers of researchers can be identified via iTrent.
|  |  |  | Create and review take-up of offer and attendance records. | 01/12/2018, 01/12/2019 | See above.
| Assess use of refreshed appraisal process to ensure that it helps manage performance and in particular how managers are assessed, developed and rewarded. | HRD Head of PSOD |  | Annual review of training for reviewers. Annual monitoring of appraisal compliance Improved satisfaction ratings with appraisal to 60% (CROS/PIRLS2019) | 01/07/2018, 2019 CROS/PIRLS2019 | Regular appraisal training workshops held for managers as part of the L&D programme. Workshops for appraisees are also available. Appraisal completions are now monitored fortnightly by senior HR colleagues and followed up within areas by HR Partner teams to ascertain the success of appraisal completion. Results are monitored through HR KPIs. Managers are reminded by e-Bulletin to upload appraisal dates and documents to My-HR. CROS 2019 indicated that 50% of respondents had had an appraisal in the last two years, and of these there was an overall 50% satisfaction rate with appraisal. Further discussions under way to see what else can be done to improve appraisal uptake and satisfaction, including links to improved appraisal training and support.
| To review current induction programme and induction toolkit materials to determine whether a specific research induction plan should be created for Researchers. (See also Principle 3&4:10) | Head of L&D |  | Induction activity reviewed after each central event and materials updated as appropriate | 3 events per year | The induction toolkit and associated resources have been reviewed and updated. A new workshop 'Preparing Impactful Inductions' workshop was delivered in February 2019 and will now be included annually in the portfolio of events from L&D. Objectives of the workshop are to share and embed good practice across the University. Participant and contributor feedback is sought after each central induction event to ensure subject relevance with clear links to the institutional strategic work streams. Faculties have also introduced faculty-level induction for new research staff, including information on research support and processes.
4. Organisational systems must be capable of supporting continuity of employment for researchers, such as funding between grants, other schemes for supporting time between grant funding, or systems for redeploying researchers within organisations where resources allow. Funders are expected to make it a priority to consider how their policies, guidance and funding can be enhanced to help employers to achieve this objective. | Make researchers more aware of access to advice and guidance provided by Careers and Employability and to potential funding from the University internship scheme. | Head of Careers and Employability Service | Head of L&D HR Partner Team Deans; CSG | Number of enquiries and outcomes recorded Careers advisor co-delivers appropriate L&D events | 01/09/2018 Annual review | L&D: Careers and employability service colleagues continued to provide 1:1 appointments for staff and contributed to the "Advancing in Academia" workshop up until 2019. The 1:1 service for staff has now been discontinued. HR business partners: The partner team works with line managers to ensure appropriate advice and guidance is provided to all staff. Systems are in place to monitor fixed term contracts and line managers are notified 6 months in advance of the contract end date. This allows sufficient time to consider options with the individual including alternative and continuing employment. All staff who are on fixed term contracts are automatically put on our redeployment register from six months before the end of their contract and remain on the register until alternative employment is found or until their contract end date. The University offers an internship scheme available to postgraduate students: ten postgrads (some students at the time, some graduates) undertook an internship between 01/08/17 and 31/07/18: PGTS offers the module "Career management skills" for postgraduate students.
| Investigate the potential for University to set up a bridging fund (time limited) to support continuity | PVC R&E | CFO | Potential established and funding stream identified Fund established | 01/12/2018 01/12/2019 | Action remains on hold in relation to the financial position. Plans in place to collate and make available information on external sources of bridging funds.
6. Researchers need to be offered opportunities to develop their own careers as well as having access to additional pay progression. Promotion opportunities should be transparent, effectively communicated and open to all staff. It is helpful if clear career frameworks for early stage researchers are outlined in organisational HR strategies. | Reward and recognise excellence in research through Staff Excellence Scheme | HR Partner Team | ADRs | Review recognition of researchers through Staff Excellence scheme, including number of nominations (See also 3&4.2) | 01/12/2018, 2019 | HR have developed clear career pathways and promotion criteria for academic staff. This information is readily available on SharePoint. We established a working group to look at career development for research-only staff. This group has now reported back to CSG and plans are in place to implement the recommendations. The Staff Excellence Award scheme has run each year since 2018 and includes categories for excellence in research. These awards provide the opportunity for staff to nominate colleagues for excellence in their field. In addition FSE holds Faculty Research Excellence Awards include category for PDRA recognition. Other faculties are also looking at faculty level schemes for recognising and rewarding research. The ADR for FBLP reviewed and reported to CSG on initiatives to reward excellence across the University in April 2019. Recommendations included developing a formal policy on research rewards and recognition linked to clear criteria.
| Ensure appropriate use of Employee Recognition Scheme | Head of PSOD |  | University Staff Survey (2018) and CROS and PIRLS surveys (2019) will demonstrate increase in satisfaction through measures of recognition. | 2018, CROS/PIRLS2019 | CROS 2019 and the internal Staff Survey 2018 gave feedback on perceptions of recognition. In CROS 2019, most research staff felt that their contribution was recognised in relation to publications and public engagement (60%) and related to knowledge transfer and commercialisation (50%). Both of the latter two were increases compared to local results in 2017. However, fewer felt that their contribution to grant and funding applications was recognised compared to 2017. Researchers have access to a number of specified awards as part of Employee Excellence Awards launched in September 2018. (Note: There is also an Employee Recognition Scheme which is different to the Staff Excellence Scheme: it is a financial award within Faculty for high performance.) The CSG lead, ADR for FBLP, has reported on institutional initiatives for rewarding excellent research. Further work planned in 2019/20 on everyday excellence, which will include rewarding researchers.
Principles 3 & 4: SUPPORT AND CAREER DEVELOPMENT
Principle 3: Researchers are equipped and supported to be adaptable and flexible in an increasingly diverse, mobile, global research environment.
Principle 4: The importance of researchers' personal and career development, and lifelong learning, is clearly recognised and promoted at all stages of their career.
Sub principle | Action | Lead | Supported by: | Success Criteria | Timescale
2. A wide variety of career paths is open to researchers, and the ability to move between different paths is key to a successful career. It is recognised that this mobility brings great benefit to the UK economy and organisations will, therefore, wish to be confident that their culture supports a broad-minded approach to researcher careers and that all career paths are valued equally. | To evaluate the current trial of offering PDRA posts in specialised areas across the institution where clusters of researchers work together on emerging research themes identified as important to the University, with the aim to better balance research groups. | R&E | Deans ADRs; Institute Directors | Researchers feel more integrated into University Research culture as measured by CROS2019 (target 50%). HR will record data on applicants, shortlists and winners of University Excellence Awards. | CROS2019 | At 23.04.19, there were 28 research-only staff listed in research institutes. The Director of the Energy and Environment Institute reports that the new Research Strategy developed at University level places researchers at the core within a flat EEI culture with mentoring and development support provided in line with the Concordat. The EEI’s investment in high performing Research Fellows enhances the culture with Research Fellows securing their own research income and developing independent research whilst also supporting PDRA’s and PhDs across the EEI with their own development. Peer to peer support and mentoring is at the heart of the EEI culture with PDRAs distributed within research clusters. There are 18 PDRAs in the EEI working in a high quality collaborative space alongside PhD and Research Fellows (currently the team is based in two locations, but once the space is completed, all the team to then be able to work collaboratively from one space). The level at which researchers felt integrated into their local research community had been maintained at 70% over the past two years, while more now also felt integrated into the wider University community (46% compared to 32% in 2017; CROS 2019). PhD investment at the University level is now aligned with CDT and DTP type investments where clusters of PhD students are grouped together in order to generate cohort cohesiveness and enhanced peer to peer support. These interdisciplinary clusters also have significant benefit enhancing the breadth of research whilst providing a thematic structure. Establishment of Research Staff Association would further support integration.
|  |  |  | PDRA numbers increase in research institutes | Annual Faculty reports, Sep 2018, 2019 | At 23.04.19 there were 28 research-only staff listed in research institutes. In FSE: Numbers have increased as follows: 2015/16 – 0 2016/17: 3 (1 in Energy and Environment Institute and 2 in Logistics and Humber Development Institute) 2017/18: 7 (4 in Energy and Environment Institute and 3 in Logistics and Humber Development Institute)
|  |  |  | Research outputs increased |  | Research outputs are listed against staff members in Worktribe and reported at Faculty level. For instance, in the Energy and Environment Institute, the increase in the number of PDRA colleagues had resulted in an enhanced quality of outputs with more papers likely to meet 3 and 4 star REF criteria, outputs becoming more international and exposure of PDRAs to external partners such as the Environment Agency.
3. Employers, funders and researchers recognise that researchers need to develop transferable skills, delivered through embedded training, in order to stay competitive in both internal and external job markets. Therefore, as well as the necessary training and appropriate skills, competencies and understanding to carry out a funded project, researchers also need support to develop the communication and other professional skills that they will need to be both effective researchers and highly-skilled professionals in whatever field they choose to enter. | Continue to enhance the portfolio of researcher development opportunities. | Head of L&D |  | Year on year increase in range of activity, with higher attendance at training and higher satisfaction of appraisal process for PDRAs | Annual review Sept by L&D to CSG | The L&D team, having the lead on research development activity, have worked closely with R&E colleagues to create a full programme of L&D activity for staff engaged in research. Annual L&D planning round commences in February each year with researcher development activity a continuing theme. In particular, activity to support the REF will be high priority. Requests for specific training received from researchers are actioned where appropriate and feasible. New online resources, produced collaboratively by and shared between a number of universities, have been made available to researchers via L&D SharePoint pages. Faculties also provide or source training and development for academic and research staff.
|  |  |  | Data available to analyse impact |  | Attendance and evaluation data is captured across the year (see below re feedback)
|  |  |  | Content of portfolio influenced by researchers, including input from Research Staff Survey (November 2017) and CROS survey, to be reflected in increased satisfaction with training provision in CROS2019 | CROS2019, Annual appraisal | The L&D team, having the lead on research development activity, have worked closely with RE colleagues to create a full programme of L&D activity for staff engaged in research. Meetings with contributors from RE have taken place to ensure a full spread of activity has been planned and will be available to support research staff in 2018/19 and 2019/20. Development themes are informed, in part, from the analysis of the CROS and PIRLS surveys thus ensuring relevance to core audiences. New events have been included and well-received e.g. facilitated writing workshops and a sessions on communicating your research to different audiences. In CROS 2019, 80% or respondents said that were encouraged to engage in personal and career development, and the proportion participating in training had increased. See below for feedback.
| Develop/enhance existing professional skills programme for researchers (not research skills) to allow professional development. Monitor Digital Capabilities project to identify areas of development for researchers | Head of L&D |  | Professional skills programme developed and implemented. Areas of development for researchers identified and incorporated into programme | Programme reviewed 01/02/2018, 2019 01/02/2019 | The process of design starts in February each year with significant stakeholder engagement over the following months. The L&D team consider skill development, professional requirements, planning for REF21 and research council criteria when designing the portfolio. The aim is to provide coverage for both research specific and professional development opportunities. No areas of development specific to researchers were identified from the Digital Capabilities Project.
| Launch revised programme | Head of L&D | R&E | Revised programme launched | 1 September 2018, 2019. | Promotion of the portfolio for the new academic year commences in the summer each year with newsletter, twitter, SharePoint and the promotional roadshow being used as vehicles to engage with staff.
| Evaluate revised programme using interim review and survey. | Head of PSOD | Head of L&D | Positive evaluations of events in research portfolio. | 01/12/2018, 2019 | Feedback is sought from participants during events, in post event evaluations, through meetings with Faculty colleagues and as part of the CROS and PiRLS surveys. Feedback is used to inform future development activity and, where possible, to make in year changes to provision. Of evaluation forms received regarding researcher development events, 90% of respondents said the event achieved its advertised objectives and 82% said that the content of the course was/will be of benefit to them, with a further 17% stating that the course was of benefit in part. New events have been included and well-received e.g. facilitated writing workshops and a session on using infographics to communicate your research.
6. Employers should provide a planned induction programme for researchers, on appointment to a research post, to ensure early effectiveness through the understanding of the organisation and its policies and procedures. They should also ensure that research managers provide effective research environments for the training and development of researchers and encourage them to maintain or start their continuous professional development | Please see Principle 2:3
| Explore barriers to participation in development events and opportunities | CSG to commission | Head of L&D | Evidence collected and reported to CSG via ADRs, including CROS2019 and focus groups | 01/09/2018 CROS2019 | L&D: The L&D team work closely with ADRs, the Concordats Steering Group, research directors and PIs to understand where improvements can be made to provide accessible, agile and relevant development activity. A blended approach to L&D supports those who are time-limited with networks and writing rooms providing additional opportunities to share best practice, apply learning and work towards specific research outputs. Feedback supplemented by surveys and discussions within faculties. 72% of respondents in CROS2019 agreed that they were treated fairly as a researcher in comparison with other types of staff in relation to access to training and development opportunities and 83% in relation to opportunities to attend conferences and external meetings.
|  |  |  | Greater take up of development opportunities. | Review annually, Sep 2018, 2019 | 80% of CROS respondents agreed that they were encouraged to engage in personal and career development, a small increase from 76% in 2017. Only 4% had spend no time on training and CPD in the last 12 months, compared to 20% in 2017. CROS results also indicated that a greater proportion had undergone training and development in the area of learning and teaching (40% compared to 18% in 2017). The numbers receiving mentoring have increased but a further 50% would be interested in this.
| Assess research environment and develop improvement plans | Deans | ADRs | Increased satisfaction (70%) with access to training and development opportunities in results of CROS and PIRLS survey 2019 | CROS/PIRLS 2019 | See figures from CROS above. In addition to training and development opportunities provided centrally, faculties also provide research support and development opportunities. For example; ·FSE is delivering: 1. a dedicated PDRA teaching module to offer lecturing experience to remove barriers to promotion; 2. Research Excellence Awards which recognise contributions by researchers at all levels via open nominations from colleagues; 3. opportunities for training on writing grants via ThinkWrite; 4. opportunities for training on writing papers via external company ThinkWrite; 5. mentoring programme open to all academics within the Faculty designed to provide focused mentoring for areas of development identified by mentees; 6. writing retreats which offer dedicated time away from campus to write papers or grants. ·FACE is introducing an Early Career Lead at Faculty Level and has reviewed its internal research support and mentoring scheme in Autumn 19. ·FBLP has an on-going review of research strategy and support for researchers, review of Academics Careers Framework transition-research plans with colleagues, and dedicated support (e.g. research funds/mentoring). Introduction of induction handbook by Faculty Operations lead/Faculty Academic Manager. ·In FHS, the new research office is involved in dissemination and also organising training. We have instigated a new research support funding mechanism in the faculty this year (2019).
| Use appraisal process to encourage professional development | HRD - Head of PSOD | ADRs/HoD/PIs | 1. Monitor research staff appraisal take-up (HR figures via iTrent) and 2. researchers' response to appraisal (Staff Survey Spring 2018, CROS 2019). Target take-up rate of appraisal of 70% and satisfaction with appraisal of 60%. | 01/12/2018, 2019 | 50% of CROS 2019 respondents (survey response rate of 30%) had had an appraisal within the last two years and about half thought it was useful. Discussion about professional development is built into the appraisal process, with follow-up action by research leads/ADR as appropriate. Managers record on I-Trent that the appraisal discussion has taken place. New L&D events on preparing for appraisal separately for both appraiser and appraisee have been developed. Faculties also monitor take-up of appraisal but it was noted that the short-term nature of research contracts may impact on the staff member's view of the value of appraisal. Further work is needed to promote the value of appraisal.
| Investigate the use of induction programmes within Faculties and share good practice across the Institution | Head of L&D | HoD | Induction programmes review and good practice disseminated; new event 'Planning for effective induction' included in portfolio for 2018/19 | 2018-09-01 | L&D: Induction programmes reviewed and good practice disseminated; new event 'Preparing Impactful Inductions' included in portfolio for both appraiser and appraisee from 2018/19. All new staff are invited to Central Induction. Materials to support local induction are available in the Induction Toolkit for Managers Inducting Research Staff. This toolkit has been reviewed in 2019. Sharing of good practice is encouraged within faculties via their Research Offices. New workshop on 'Preparing Impactful Inductions' has been developed and delivered.
7. Employers and funders will wish to consider articulating the skills that should be developed at each stage of their staff development frameworks and should encourage researchers to acquire and practice those skills. For example, researchers may be given the opportunity to manage part of the budget for a project, or to act as a mentor or advisor to other researchers and students. | Continue to promote RDF to researchers and their research leaders as a useful tool to plan and action development as a researcher. Integrate with new “on-boarding” processes. Include appropriate content within updated performance management training. | Head of L&D | ADRs | RDF used to identify skills sets required by individual researchers and consideration given to the opportunities that can be made available to support acquisition of those skills | Annual review Dec 2018, 2019 | Information about the RDF has been disseminated via L&D promotional presentations and L&D newsletters. The RDF is included on the L&D Toolkit of Resources on the SharePoint site. Information is also disseminated through Faculty newsletters etc. The RDF is used directly in two L&D events: 'Introduction to the RDF' and 'Advancing in Academia'. The RDF can be used in appraisals for career development. The RDF has also been promoted in faculties. CROS 2019 indicated that 40% (38% in 2017) of respondents had some understanding of the RDF and a further 11% were aware of it but did not know the detail.
|  |  |  | Increased take up of RDF licenses | Annual review of RDF licences in Jan 2018, 2019 | New postgraduate students use the RDF for one of the assignments for the Modern Researcher course, but students struggled in 2018 to log on to use the planner, so they engaged with the RDF outside of the online planner. In 2019 they continued to use the RDF in other formats. Staff have engaged with the RDF through L&D events etc. but in CROS 2019 the proportion of respondents using the RDF had dropped from 18 to 11%; these values may reflect changes in the demographics of the respondents. Note: The number of licences used does not necessarily relate to the number of people using the RDF in other formats. Researchers engage with the RDF in workshops, but relatively few engage with the RDF planner and hence the University has decided not to continue the subscription.
| Include discussion of career development in the annual appraisal process | HODs |  | Feedback from annual appraisal process Increased satisfaction with appraisal process to 60% evidenced in CROS 2019 | Dec 2018, 2019 CROS2019 | Career development is discussed in appraisals and staff are encouraged to consider career development on an ongoing basis. Appraisals take place on an annual basis with an interim 6-montly report. 50% of CROS 2019 respondents (response rate of 30%) had had an appraisal within the last two years and about half thought it was useful. New L&D events on preparing for appraisal for both appraiser and appraisee have been developed. Faculties also monitor take-up of appraisal but it was noted that the short-term nature of research contracts may impact on the staff member's view of the value of appraisal.
8. Employers also should provide a specific research career development strategy for researchers at all stages of their career, regardless of their contractual situation, which should include the availability of mentors involved in providing support and guidance for the personal and professional development of researchers. All researchers should be familiar with such provisions and arrangements. | As part of the revised training programme for researchers, review the current mentoring arrangements to ensure research specific requirements are catered for. | CSG | L&D | Researchers have access to a flexible and appropriate mentoring scheme that enables career development. Take-up monitored via ADRs and satisfaction with scheme measured via CROS2019. | 2018-12-01 | Mentoring is available across the University. Further guidance is being prepared as the schemes develop. A review of mentoring schemes for research-active staff was carried out in June 2019; this recommended that the scheme should be voluntary, but uptake should be monitored, formats in addition to 1:1, such as peer-support and special-interest groups, should be considered and that specific issue-based mentoring relationships should be encouraged. 28% of CROS 2019 respondents said that they had received mentoring and a further 48% said that they would like to be mentored.
| To work with the HR business partners to identify career pathways for researchers and actions to implement. | HR Partner Team | DoR ADRs Head of L&D | Potential career pathways are clearly articulated | 2018-12-01 | Academic Careers Framework (ACF) for academic staff was approved at JNC March 2019. This included a research path for academics but did not cover research-only staff. Hence, the Concordats Steering Group (CSG) commissioned a Working Group to review and make recommendations for career progression for researchers. This group reported to CSG in September 2019 and recommended developing a career development framework specific to researchers.
| Creation of career development frameworks for researchers | HR business partner |  | Career development frameworks created and made available | 2019-07-01 | Career pathways continue to be developed with specific routes of progression being identified for researchers. This work will link into learning and development, appraisals and workload planning.
9. Research managers should actively encourage researchers to undertake Continuing Professional Development (CPD) activity, so far as is possible within the project. It should be stressed that developmental activity can often have a direct impact on the success of the project, by distributing work, taking advantage of individual strengths and talents, and increasing the skill and effectiveness of researchers in key areas such as writing for publication or communicating with a wider audience. Funding bodies acknowledge that the training of researchers is a significant contribution to research output and they encourage employers and mentors to adopt these practices. | Researchers are able to access support to discuss CPD activity and have access to formal development as required. | Deans | ADRs;PIs, HoD | Improved responses in both CROS and PIRLS surveys, e.g. number of days used for CPD activity, increased satisfaction with appraisal process | 01/09/2018, 2019 | CROS 2019: In the past 12 months (or since taking up their current position if that was more recent), only 4% of respondents had spent no time on training or CPD (compared to 20% in 2017), 78% had spent between one and five days and 17% had spent more than five days. 59% said that appraisal was useful in leading to training/CPD and 45% in helping you focus on career aspirations. Mentoring programmes are in place and CPD can be discussed in appraisals (see above). Research staff can attend internally-provided workshops, such as 'Advancing in Academia', and Faculty-led initiatives as appropriate. See above for responses on appraisal.
(See also Principle 3&4:6)
| Revised training programme for researchers to have clearly articulated learning pathways and to clarify training that is: - Must have/do - Optional - Enhanced | Head of L&D |  | Compliance with mandatory training monitored and reviewed. Evaluation of optional events demonstrates relevance. | 01/09/2018, 2019 | Mandatory training maps were launched across the University in 2019. Regular compliance reporting provided to all areas. A development programme specific for researchers has been proposed (see above): this would be available via the L&D SharePoint site.
|  |  |  | Evaluation of relevance 75% positive on feedback forms |  | Over a 13 month period 94% of those who gave feedback on research-related training and development events agreed that the event had achieved its advertised objectives and 82% said the content was or would be of benefit to them.
10. Researchers should be empowered by having realistic understanding of, and information about, their own career development and career direction options as well as taking personal responsibility for their choices at the appropriate times. Employers should introduce appraisal systems for all researchers for assessing their professional performance on a regular basis and in a transparent manner. It is important that researchers have access to honest and transparent advice on their prospects for success in their preferred career. | Use appraisal process in a flexible way to accommodate specific needs of researchers to enable a meaningful process (see also action 2.3) | HRD - Head of PSOD | Deans, ADRs, HoD, PIs and L&D | Increased satisfaction with the value of appraisal in results of CROS and PIRLS survey 2019 e.g. to 60% as useful overall for both groups. | CROS/PIRLS 2019 | New appraisal training developed and rolled out. See above. Launched ADR (Appraisal and Development Review) in place of SPDR (Staff Performance and Development Review), including revised guidance and a single use form to capture requirements and progress.
| Assess the level of interest in forming a new Research Staff Association (RSA) and, if there is a demand, initiate the process of setting one up. | Head of L&D |  | Requirement for RSA assessed. Set up with help from L&D if required | 01/07/2018 01/12/2018 | We had interest in forming a RSA but no-one came forward who felt that they were in a position to take a role on the steering group at present. However, there was sufficient interest to revisit this in 2020 and consider if L&D can offer more support.
12. Employers will ensure that where researchers are provided with teaching and demonstrating opportunities as part of their career development, suitable training and support is provided. | Continue to provide learning and teaching training and support for researchers with teaching and demonstrating opportunities. | Director of L&TE | L&D | Credit-bearing learning and teaching module, providing a route to Associate Fellowship of the HEA, available for PDRA staff in 2018 to ensure that they gain appropriate lecturing experience. Take-up and value evaluated successfully, reported to CSG. | 01/12/2018, 2019 | (1) The credit-bearing module Professional Practice in Teaching and Learning in HE ran for the first time in 2017-18 with a cohort of 16 PGRs. From 2018-19 there will be two cohorts per trimester- one of PGRs and one of PDRAs. For the PGRs, the credit they gain through successful completion of the module will count towards the Graduate School/Doctoral College’s Postgraduate Training Scheme. Accreditation of the module was pursued earlier than the next 2020 reaccreditation round so that PDRAs and PGRs would gain accreditation as AFHEA in addition to the academic credit. 13 PGRs and 2 PDRAS commenced the module in February 2019; 9 PGRs and 2 PDRAs commenced the module in September 2019; the 20 credit module can count towards the PGTS (Postgraduate Training Scheme); 21 module completers have gone on to gain AFHEA status through the University's DARTE scheme (September 2019). (2). Passport to University Teaching (the University's mandatory training for those who wish to teach; non-credit bearing, non-accredited): 2019-20. 6 x 1 day workshops are offered during the 19-20 academic year. 22 PGRs (including lab demonstrators) attended the first workshop in September. 2018-19: to date 92 PGRs and PDRAs have attended workshop sessions. (3) All the workshop sessions on teaching and learning development through LTEs Academic Professional Development Framework are open to PDRAs involved in teaching. Additionally, some PDRAs are eligible for the PCAP programme or DARTE scheme, depending on the number of hours they are teaching. (4) A new Canvas site - Learning and Teaching Essentials was launched in June 2019 offering just-in-time teaching support on all aspects of teaching, learning and assessment; the site is open to all researchers who teach and is also linked from the L&D SharePoint pages. (5) 23 PDRAs and PGRs attended a session Teaching Skills for Researchers in May 2018 which focussed on evidencing teaching skills (and transferable skills) in job applications.
14. Mentoring arrangements should be supported by employers as a key mechanism for career development and enhancement. | Monitor uptake of coaching opportunities by research staff, including internal offer by L&D and through the Yorkshire Accord Scheme | Head of L&D |  | Increase in take-up of offer by researchers. | 01/12/2018, 2019 | The Autumn 2018, Spring 2019 and Autumn 2019 recruitment round elicited no applications for centrally provided coaching opportunities from research active staff. Head of PSOD and Head of L&D to discuss future targeted promotions. 28% of CROS 2019 respondents said that they had received mentoring and a further 48% said that they would like to be mentored.
| Research mentoring schemes will be implemented across all faculties in 2018. | Deans | ADRs | All Faculties will have research mentoring schemes in place. Monitored annually. | 01/12/2018, 2019 | Faculty mentoring schemes in place and promoted. For example, in FSE there are currently 25 mentoring relationships which have been established within the Faculty. The scheme remains open to interested individuals. 31 staff have volunteered as mentors. 13 members of staff have received 2 days' worth of training to become mentoring experts. A report to CSG in Dec 19 recommended a University-level mentoring scheme for all academic staff.
Principle 5: RESEARCHERS' RESPONSIBILITIES
Individual researchers share the responsibility for and need to pro-actively engage in their own personal and career development and lifelong learning.
Sub principle | Action | Lead | Supported by: | Success Criteria | Timescale
1. Researchers are employed to advance knowledge and should exercise and develop increased capacity for independent, honest and critical thought throughout their careers. | Continue to monitor the implementation of the action plan for the Concordat to Support Research Integrity | CSG | Deans; R&E; GS; ADRs to communicate action plan to faculties | Local areas report on progress to URC via CSG | 01/09/2018, 2019 | Research integrity is included in the University mandatory training map: all staff involved in carrying out research are required to complete the online Research Integrity module. Training is also mandatory for all funding applications (internal and external). Review of data provided and targetted messaging to colleagues (e.g. via research lead and HSG briefing). Records of completions of the online module are kept by Learning and Development. This is then followed up with face-to-face sessions within Faculties - attendance records are maintained by Faculties. Training is only recorded as complete when researchers have completed both the online module and faculty workshops. All PGR students now receive research-integrity training through a programme co-ordinated by the Graduate School (now the Doctoral College).
| Launch online Research Integrity Module | Head of L&D CSG |  | Module launched Take up by all researchers complete. New staff advised of requirement through Mandatory Training Map | 01/02/2018 31/12/2018 | L&D report produced 17.10.19 shows 704 successful completions of the online research integrity course. In CROS 2019, 76% of respondents (research-only staff) had already completed training in ethical research conduct and 13% wanted to. We need to understand why 11% (5 people) stated that this was of no interest to them.
|  |  |  | University able to evidence compliance to HEFCE | Ongoing | The Research and Governance Office report annually regarding compliance to Research England, as evidenced in our annual research integrity report.
| Researchers output to be monitored on an annual basis to ensure that output does not diminish over time | Deans | ADR | Individuals research outputs are maintained over sustained periods - monitored by Annual Research Report within Faculties. Information recorded in data management system WORKTRIBE | Ongoing | Researcher outputs are monitored at faculty level through the appraisal process and through annual reports which are recorded via WorkTribe. Monitoring also occurs through faculty research offices as part of REF preparations. Reports provided to research leads 1-2 times per year. Includes publications, applications and KE activities.
2. Researchers should develop their ability to transfer and exploit knowledge where appropriate and facilitate its use in policy making and the commercialisation of research for the benefit of their employing organisation, as well as the wider society and economy as a whole | Promote and communicate opportunities for developing awareness of commercialising research and knowledge transfer | Head of Commercialisation; FDBEE | Deans, ADRs, L&D, HR to promote through their existing processes and programmes | Increased awareness and opportunities to take part as measured in CROS survey to achieve 75% for awareness. |  | The new Academic Career Framework launched in April 2019 includes 'Knowledge, Innovation and Engagement' as one of the three Core Career Domains. Each faculty has a Director of Business Engagement and Enterprise (FDBEE) who coordinates and facilitates commercial research activity through 'innovation landscape' meetings, KTP workshops etc., liaises with the Dean and ADR, and sits on Faculty Research Committee. Competition for HEIF funding (https://re.ukri.org/knowledge-exchange/the-higher-education-innovation-fund-heif/) is held within faculties. The University is part of the THYME collaboration between the Universities of Teesside, Hull and York to boost the bioeconomy across Yorkshire, the Humber region and the Tees Valley (https://thyme.biovale.org/about/). Open meetings have been held to promote networking, provide information on funding opportunities and entrepreneurship training. Head of Commercialisation ran the first of a number of 'Being Enterprising in your Research' breakfast briefings with FHS in September 2018. Planned to roll this out for the other Faculties in 2019. Each faculty runs a HEIF (Higher Education Innovation Fund) challenge to fund projects involving knowledge exchange. For example, in FHS this has culminated in a number of staff engaging now both in facilitating the research exploitation and applied research processes and building knowledge networks including palliative care, clinical psychology, sports, health and exercise science including physio. The outcomes from the HEIF projects were showcased at a Faculty workshop (October 2019) and this was an excellent opportunity for the staff involved to articulate further the impacts and value of knowledge exchange activities for health. The challenge has enabled health sciences to build further its internal capability to support further staff development about knowledge exchange; as well as encouraging staff to take forward new enterprise ideas and initiatives.
| Researchers encouraged to consider impact when preparing grant applications | ADR | HoD | No of applications including effective reference to impact as monitored within Faculties | 01/12/2018, 2019 | Impact content in grant applications is being monitored at faculty level and all applications undergo review by research committee. Training on research impact is included at faculty level and provided centrally through L&D.
| Review training on making grant applications, included as part of revised training programme for researchers | Head of L&D | R&E | Continued inclusion of funding workshops in programme for researchers | 01/09/2018, 2019 | L&D: Planning for the 2018/19 portfolio commenced in February 2019 with researcher development activity a continuing theme. In particular, activity to support the REF will be high priority. GRANTfinder training has moved to online provision. Worktribe training is delivered via drop-in clinics and one-to-ones
3. Researchers should recognise their responsibility to conduct and disseminate research results in an honest and ethical manner and to contribute to the wider body of knowledge | CSG to identify clear measures to evaluate the effectiveness of implementation of Concordat to Support Research Integrity | CSG | ADRs | Measures and training required under Concordat are delivered | Annual Review 2018, 2019 | Currently measured by training compliance rates recorded at faculty level, with completion of the online Research Integrity module recorded by L&D. Staff who have not completed the training are no longer eligible for faculty research funding to support their activities. In CROS 2019 76% of respondents (research-only staff) reported completed training in ethical research conduct and 13% wanted to.
| Clear dissemination of good practice policies on website and/or sharepoint | Marcomms | CSG | University website and intranet contains up to date and relevant material | Annual Review 2018, 2019 | Policies are available externally on the Research Integrity and Governance web pages https://www.hull.ac.uk/work-with-us/research/governance/research-integrity-and-governance.aspx and internally on the Research Integrity and Ethics SharePoint pages
| Online Research Integrity module launched Feb 2018 to be supported by Faculty-led initiatives | L&D | R&E | All researchers have completed course. Researchers confirm awareness of Code of Good Research Practice through appraisal. Increase in awareness of Concordat to Support Research Integrity in CROS 2019. | Annual review Dec 2018, 2019. CROS 2019 | Research integrity is included in the University mandatory training map. The online module is supported by faculty-led workshops etc. as above. There were 704 successful completions of the online research integrity course at 17.10.19. 63% of respondents in CROS 2019 were aware of the Concordat to Support Research Integrity, 76% reported undertaking training in ethical research conduct and 13% would like to undertake this training.
5. Researchers should recognise that the primary responsibility for managing and pursuing their career is theirs. Accordingly, they should identify training needs and actively seek out opportunities for learning and development in order to further that career and take personal responsibility for their choices. Research managers and employers also have a responsibility | Communicate the expectations of the University that researchers should be proactive in engaging with their career development through appraisal and L&D workshops | HRD - Head of PSOD | Deans,ADRs, HoD, PIs and L&D | Effectiveness of message evaluated using data analytics and results of the Staff Survey 2018, CROS 2019 | 2018, 2019 | Researchers are encouraged to reflect on their own development as part of the appraisal process and look for areas of development that would best suit their careers. 94% of respondents in CROS 2019 agreed that they take ownership of their career development and 80% said that they were encouraged to engage in personal and career development. Some aspects of training and development are mandatory, such as research integrity, but the rest is responsive.
6. Researchers should ensure that their career development requirements and activities are regularly discussed, monitored and evaluated throughout the year in discussion with their research manager and mentor, and that they commit themselves fully to all such activities. Researchers are encouraged to record their Personal Development Planning (PDP) and CPD activities, a log of which may be presented to current and future employers as appropriate. | Use of RDF as a method of recording CPD is promoted as part of revised performance management process. | CSG | ADRs/L&D | Increased take-up of RDF licences. CSG to support this programme and review uptake data with data from L&D as administrators of the RDF | Annual Review of RDF licences Jan 2018; 2019. | The L&D team promotional presentations include specific reference to the RDF as a useful diagnostic. The team deliver "an introduction to the RDF" as part of the L&D portfolio, again raising awareness of the toolkit. The RDF has been highlighted in other workshops, such as 'Advancing in Academia'. A review of licence holders to remove inactive users and those who have left the University has reduced the number of active users of the planner. However, some individuals will be using the RDF as a planning tool without using the planner itself. The Graduate School (Doctoral College) used the RDF offline in 2019-20. Almost 60% of respondents in CROS 2019 maintained a formal record of their CPD activity but only 11% reported using the RDF for this. Researchers engage with the RDF in workshops, but relatively few engage with the planner and hence the University has decided not to continue the subscription.
| Enhance the appraisal system to act as a trigger for career development discussion and recording of the conversations using the RDF. | HRD - Head of PSOD |  | Increase satisfaction with appraisal (to 60% in CROS 2019). Higher take up of RDF licenses (as reported to CSG annually) | Dec 2018; 2019 | Career development discussions are now actively encouraged as part of appraisal reviews and there is a section on the appraisal form that prompts this discussion. The benefits of the RDF to be promoted as part of ongoing workshops and communications with Researchers. The L&D team have designed a number of variants of appraisal training for different target groups, including academics and academic managers. Content includes specific reference to the RDF where appropriate and will be aligned with the University Academic Careers Framework (approved at JNC March 2019). Active monitoring of appraisal completion is conducted fortnightly. Revised appraisal training should help to address inconsistencies of practice and help promote higher quality conversations as part of the process.
Principle 6: DIVERSITY AND EQUALITY
Diversity and equality must be promoted in all aspects of the recruitment and career management of researchers
Sub principle | Action | Lead | Supported by: | Success Criteria | Timescale
3. It should be emphasised that the demanding nature of research careers has a disproportionate effect on certain groups. We strongly recommend that all members of the UK research community actively address the disincentives and indirect obstacles to retention and progression in research careers which may disproportionately impact on some groups more than others. | Impact assess University wide initiatives and incentives for identifying, retaining and developing researchers for report to URC via CSG. | Head of ED&I | Deans | Review completed, evaluation made and actioned | To meet Athena SWAN review timescales | This is ongoing to measure EDI initiatives against progress. Much of the equality work is being tied to respective equality charters like Athena SWAN and the Race Equality Charter. More work has been identified to engage and connect better with the research community. Two schools within the Faculty of Science and Engineering were awarded Bronze Athena SWAN Charter in November 2018.
| Ensure synergy with Athena SWAN to complement the work being done across the University. | Head of ED&I | HR; ADRs, Faculty AS champions | Measure as part of relevant surveys e.g. CROS and PIRLS | CROS/PIRLS 219 | Athena SWAN plan should align areas of concern with actions and activities. Ongoing as part of faculty/department Athena SWAN applications.
4. Employers should ensure that the working conditions for researchers provide the flexibility necessary for successful research performance in line with legal requirements. Employers should recognise that for parents and others who have taken career breaks, including parental leave, have worked part-time, or have taken atypical routes into research, the “early career” period may be prolonged, and this may be a time where the risk of attrition from the research path is most acute. Working conditions should allow both female and male researchers to combine family and work, children and career. | Continued development of positive research environments where flexibility is encouraged and awareness of individual challenges can be accommodated. | Deans | ADRs | Positive data from Staff Survey suggesting more flexible responses are made (e.g. fewer individuals identify problems). Research staff clearly identified in survey responses. | 2018-07-01 | Faculties have introduced additional workshops and facilitation e.g. mentoring training, bid writing, work-life balance. Faculties have conducted surveys which include questions about the research environment and used this information to review policies and support provision. 76% of CROS 2019 respondents said that they were satisfied with their work-life balance. 70% agreed that they were treated fairly as researchers in comparison to other types of staff in relation to requests for flexible working.
|  |  |  | Data from CROS and PIRLS 2019 suggest increasingly positive and increasingly similar attitudes to their employment experience | CROS/PIRLS 2019 | CROS 2019 data indicated an increase from 2017 in the proportion of respondents who felt that staff at the University were treated fairly in relation to, for example, day-to-day treatment (increase from 67 to 74%), career progression and promotion (increase from 40 to 44%) and reward (increase from 35 to 41%).
|  |  | HR partners | Monitor records of flexible working requests and outcomes | Annual review, Dec 2018, 2019 | In July 2019 no research-only staff had requested flexible working, however 41 requests had been made by staff on teaching and research contracts, of which 40 were agreed in full and one agreed in part. Not all flexible working requests are captured centrally so this process is being reviewed and regular monitoring will then be carried out. The flexible Working policy has been revised to provide clarity regarding the monitoring of requests. This was approved by the UoH Policy Working Group in October 2019 and circulated as a HR Brief to all managers accordingly to make them aware of the changes to the policy. As at December 2019, no research-only staff on an FTC had requested flexible working, however 4 requests had been made by staff on teaching and research contracts on continuing contracts, along with 2 requests from research-only staff on continuing contracts, all of which were agreed in full.
|  |  |  | Actively promote externally funded returning-to-work fellowship programmes. Consider setting up internal funding for returning-to-research fellowships. | Review annually. Promote as opportunities present. | Information about returning-to-work fellowship programmes has been circulated but, as these schemes are usually dependent on internal as well as external funding to support candidates, they are subject to budgetary considerations.
| Ensure alignment with Athena SWAN action plan | Head of ED&I |  | Aligned delivery programmes | 01/07/2018, 2019 | Athena SWAN aligns responsibility for these actions and activities with HRD.
10. Employers should also consider participation in schemes such as the Athena SWAN Charter, the Juno Project and other initiatives aimed at promoting diversity in research careers. | The University has been awarded the Athena SWAN Bronze Award. The University signed up to University wide applications for departments or schools | HoDs |  | Number and success of departmental or school applications | Ongoing annual review Sept 2018, 2019 | The University received confirmation of retention of Bronze award in October 2018. The current award is valid through to April 2022. Hull York Medical School was awarded the Athena SWAN Silver award and has achieved renewal of this award to 2023. School of Environmental Sciences & School of Maths and Physical Sciences from Faculty of Science and Engineering both awarded Bronze Athena SWAN Charter in November 2018.
Principle 7: MONITORING AND EVALUATION
The sector and stakeholders will undertake regular and collective review of progress in strengthening the attractiveness and sustainability of research careers in the UK.
Sub principle | Action | Lead | Supported by | Success Criteria | Timescale
1. The implementation of the Concordat’s principles will lead to greater integration of researchers into the mainstream management and career development structures of their employing organisations. The aim of this section is to promote implementation through a collective commitment to reviewing its progress. | Develop an explicit communication strategy to ensure greater awareness of the Concordat Agenda | Marcomms | CSG | Website and/or intranet populated with information that is relevant, accessible and up-to-date | 01/06/2018, review June 2019 | An information series on the concordats and related initiatives have been featured in the L&D newsletter with information also on research governance SharePoint pages. Information has also been shared on the L&D SharePoint pages. There was an increase in knowledge and understanding around the REF from 62% in 2017 to 74% in CROS 2019. Knowledge and understanding of other initiatives was similar in the two surveys. Going forwards this information will be incorporated into a new researcher development programme.
|  |  |  | Use data analytics to evaluate access and use of site | September 2018, 2019
| Consider any developments arising as a consequence of the Concordat Review | CSG | R&E, L&D | Changes reported to CSG and implications for CSG agenda considered | 2018 | The R&E team coordinated the University response to the review of the Concordat in January 2019. CSG has been apprised of the recommendations of the Expert Review Panel (June 2018). The University became a signatory of the new Concordat in November 2019 and will begin working towards principles therein. Researcher development activity a continuing theme in the L&D portfolio. In particular, activity to support the REF will be high priority.
4. The signatories recognise the value of innovation in practices and of sharing practice between institutions and aim to promote these throughout the implementation and review process. | The University to maintain its membership of the Vitae organisation. | R&E | CSG; Head L&D | Membership retained and use of Vitae website promoted during Induction and the revised training programme. Assess usage through Vitae's figures of registered University of Hull users. | Annual review Sept 2018, 2019 | Membership retained and use of Vitae website promoted during Induction and the revised training programme. There has been an 18% increase in Vitae registered users from the University of Hull from 269 at 22.05.18 to 317 at 27.08.19 (Vitae data).
| To maintain a regional and national presence at Vitae events and networks | Head of L&D | GS | Events and networks attended and learning is shared. | Ongoing | Member of L&D staff attended REDS (Researcher Education and Development) conference October 2018 and continues to attend NERDS (Network of Expert Researcher Developers) events and where appropriate, learning from events is shared in order to disseminate best practice. Graduate School/Doctoral College: PGTS leader to continue attending VITAE events and to act as liaison. Several members of GS team are involved with UKCGE.
The funding signatories will consider aligning their support for transferable and career development skills. It is expected that Vitae, the national programme dedicated to realising the potential of researchers, funded by the Research Councils, will play a major role in innovating, sharing practice and enhancing the capability of the sector to implement aspects of the Concordat, as well as establishing strategic partnerships between funders. | To maintain good practice sharing opportunities through the Network of Expert Researcher Developers (NERDS) | Head of L&D | GS | Attend NERDS meetings and share learning. | Ongoing, 3-4 meetings per year | The NERDS group have been developing shared materials for researcher development. Each webinar has been promoted to our research staff using the Contract Research Staff email list and each is followed by online discussion. These resources have been collated and referenced from our researcher development pages. Hull contributed a webinar on Academic Careers to this series in January 2019.
| To continue to promote and support the use of the RDF to research students and staff and include in on boarding material for both staff and students. | Head of L&D | HR ADR CSG GS | On boarding material for staff and students includes information on the RDF and its use in career planning/development. Increased awareness of RDF to 50% in CROS2019. | Annual Review Dec 2018; 2019; CROS2019 | L&D offer an introductory workshop on the RDF each year and incorporate its use into the Advancing in Academia workshop. Information on the RDF is available via the L&D SharePoint pages and has also been included in some faculty activities around career development and mentoring and also in the L&D newsletter. Just over 50% of respondents in CROS 2019 were aware of the RDF: 40% of respondents said that they had some understanding of the RDF and an additional 11% were aware but not in detail.
5. Under public sector equality schemes, employers are required to monitor equality and diversity indicators for their researchers. This section focuses on the co-ordination and enhancement of existing information collection and not on the creation of additional data. There is a strong presumption that in implementing the Concordat, significant emphasis will be placed on the use of existing data and information sources and on the sharing of good practice between institutions and to provide evidence of its impact. | Continue to take part in the national CROS and PIRLS surveys | CSG to commission | L&D | Surveys conducted and outcomes presented to URC and used to inform future planning. | CROS/PIRLS 2019; Staff Survey 2018 | The University participated in CROS 2019 with a 30% response rate. This was reported to the Concordats Steering Group in November 2019. PIRLs questions were included in the University's Staff Survey 2018. It has been agreed to run CROS and PIRLs biennially going forwards. Note: a draft CROS survey based on the new Concordat may be run by Vitae in 2020.
| Develop the use of focus groups to add additional insights to survey data across the University and through networks with other HEIs | CSG to commission | ADRs | Researchers are consulted on pertinent and relevant issues relating to research across the University and beyond. | As required for specific purposes | Opportunities for researchers to feedback take place at faculty research fora and in ADRs meetings with research groups.
| Equality and Diversity data presented to URC for profiling of researchers and impact/risk assessment. | Head of ED&I | URC | Where ED&I data highlights trends which require further investigation, action is then taken to address the relevant issues. | Annual review, Date CROS/PIRLS 2019 | CROS 2019 data raised some issues which were reported to the CSG. These issues will be addressed through the HR Excellence in Research Action Plan 2020-22. The annual staff data report on EDI was presented to the EDI Committee in January 2020.
HR Services Team
| Integration of activities with Athena SWAN | Head of ED&I |  | Limited additional datasets | Annual review, Sep 2018, 2019 | Work ongoing to ensure integration with Athena SWAN (see above)
Abbreviations
ADR | Associate Dean for Research
CFO | Chief Finance Officer
CPD | Continuing Professional Development
CROS | Careers in Research Online Survey
CSG | Concordats Steering Group
DoR | Director of Research
ED&I | Equality, Diversity and Inclusion team
FTC | Fixed term contract
FDBEE | Faculty Director of Business, Engagement and Enterprise
FACE | Faculty of Arts, Cultures and Education
FBLP | Faculty of Business, Law and Politics
FHS | Faculty of Health Sciences
FSE | Faculty of Science and Engineering
GS | Graduate School, now renamed Doctoral College
HEIF | Higher Education Innovation Fund
HoD | Head of Department
HR | Human Resources
JNC | Joint Negotiating Committee
LTE | Directorate for Learning and Teaching Enhancement
L&D | Learning and Development
MarComms | Marketing and Communication department
PGTS | Postgraduate Training Scheme
PI | Principal Investigator
PIRLS | Principal Investigators and Research Leaders Survey
PSOD | Head of People Services and Organisational Development
PVC-RE | Pro-Vice-Chancellor for Research and Enterprise
RDF | Vitae Researcher Development Framework
REF | Research Excellence Framework
R&E | Research and Enterprise Team
RIS | Research Information System
R&S | Recruitment and selection
UASSG | University Athena Swan Steering Group
UREC | University Research and Enterprise Committee